## Sheet1
Day | Task | Team Member | Responsible for
1 | Create project repo, add team members, and set up permissions | Naveen | Project repo management, team member addition, and permission setup
1 | Research and document project requirements | Neeraj | Functional and non-functional specifications, requirements gathering
1 | Assist Neeraj in researching and documenting project requirements | Saurabh | Requirements gathering and documentation
1 | Set up project infrastructure (e.g., Docker Compose, environment variables) | TBD | Project infrastructure setup
2 | Design overall architecture of the project | Naveen | Frontend, backend, and infrastructure components
2 | Document architecture design | Neeraj | Component diagram, data flow, and documentation
2 | Assist Neeraj in documenting architecture design | Saurabh | Documentation and architecture design
2 | Develop a plan for testing and quality assurance | TBD | Testing and QA plan development
3 | Design API endpoints | Naveen | Request and response formats, API endpoint design
3 | Document API design | Neeraj | Endpoint table, error handling, and documentation
3 | Assist Neeraj in documenting API design | Saurabh | Documentation and API design
3 | Implement API security measures (e.g., authentication, authorization) | TBD | API security implementation
4 | Plan deployment strategy | Naveen | Environment variables, Docker Compose build/run steps, and deployment plan
4 | Document deployment plan | Neeraj | Model download commands, cleanup steps, and documentation
4 | Assist Neeraj in documenting deployment plan | Saurabh | Documentation and deployment plan
4 | Develop a plan for monitoring and logging | TBD | Monitoring and logging plan development
5 | Develop YOLO-v5 and Llama-7B models | Naveen | Quantization and inference code
5 | Test models | Neeraj | Damage detection, cost estimation, and testing
5 | Assist Neeraj in testing models | Saurabh | Testing and model development
5 | Implement model serving and deployment | TBD | Model serving and deployment
6 | Develop frontend code | Naveen | React SPA, image upload functionality
6 | Test frontend code | Neeraj | Chat UI, image upload functionality, and testing
6 | Assist Neeraj in testing frontend code | Saurabh | Testing and frontend development
6 | Implement frontend security measures (e.g., input validation, sanitization) | TBD | Frontend security implementation
7 | Integrate frontend and backend components | Naveen | API endpoints, model inference, and integration
7 | Deploy application to cloud platform | Neeraj | Environment variables, Docker Compose build/run steps, and deployment
7 | Assist Neeraj in deploying application | Saurabh | Deployment and application development
7 | Monitor and log application performance | TBD | Monitoring and logging